Project Task Scheduling with Limited Resources and Dependencies

1. Problem Definition

Project scheduling assigns a set of tasks to limited resources while satisfying precedence constraints and minimizing the overall project completion time.

Let:

\(T = \{T_1,T_2,\ldots,T_n\}\) = set of tasks

\(R = \{R_1,R_2,\ldots,R_m\}\) = available resources

\(d_i\) = duration of task \(T_i\)

\(r_i\) = resources required by \(T_i\)

\(P_i\) = set of predecessor tasks of \(T_i\)

A task can start only when:

All its predecessors have completed.

Sufficient resources are available.

It does not overlap with another task using the same limited resource.

2. Constraints

Resource Constraint

If the available resource capacity is \(C\):

$$ \sum_{T_i\ active} r_i \leq C $$

Example:

Task	Duration	Resource Required	Dependencies

T1	3	2	—

T2	2	1	T1

T3	4	2	T1

T4	2	1	T2, T3

T5	3	2	T3

Assume total resource capacity:

$$ C=3 $$

Therefore, T2 and T3 can execute simultaneously because \(1+2=3\), but two tasks requiring 2 resources each cannot execute together.

3. Precedence Constraints

The dependency graph is:

$$ T1 \rightarrow \{T2,T3\} $$ $$ T2,T3 \rightarrow T4 $$ $$ T3 \rightarrow T5 $$

Thus:

T1 must finish before T2 and T3.

T2 and T3 must finish before T4.

T3 must finish before T5.

These dependencies reduce the number of feasible schedules.

4. Backtracking-Based Solution

Backtracking builds a schedule incrementally. At every step, it selects an eligible task and tries to schedule it.

Basic Algorithm

BACKTRACK(schedule, completed, time, resources):

if all tasks are completed:

save schedule

return

eligible = tasks whose predecessors are completed

for each task T in eligible:

if resources_required(T) <= available_resources:

assign T to the earliest feasible time

update resources and completed tasks

BACKTRACK(new_schedule, new_completed,

new_time, new_resources)

undo assignment

5. Pruning Techniques

Backtracking can become expensive, so invalid branches should be eliminated early.

A. Resource Pruning

If:

$$ r_i > C $$

the task can never be scheduled and the branch is immediately rejected.

B. Precedence Pruning

A task is never scheduled until all predecessors are complete.

For example, scheduling T4 before T2 or T3 is rejected immediately.

C. Deadline/Lower-Bound Pruning

If the current completion time plus the minimum remaining processing time exceeds the best solution already found:

$$ currentTime + lowerBound \geq bestTime $$

prune the branch.

D. Symmetry Pruning

If two tasks have identical resource requirements, duration, and dependency relationships, exploring equivalent orderings is unnecessary.

E. Resource-Conflict Pruning

If scheduling a task would make:

$$ \text{used resources} > C $$

the branch is discarded without further exploration.

6. Example Schedule

For the given tasks and \(C=3\):

Time 0–3

T1 executes.

Resource usage:

$$ 2/3 $$

Time 3–5

T2 and T3 can execute together:

T2 = 1 resource

T3 = 2 resources

Total:

$$ 1+2=3 $$

Time 5–8

T5 executes because T3 has completed.

T4 must wait until both T2 and T3 have completed. It can therefore execute from 5–7.

Depending on the scheduling objective and resource availability, T4 and T5 may be scheduled together only if:

$$ 1+2=3 $$

which is feasible.

One optimal schedule is therefore:

Time	Tasks	Resources

0–3	T1	2

3–5	T2 + T3	3

5–7	T4 + T5	3

Project completion time = 7 units.

7. Effect of Constraints on Feasibility

Constraints can significantly reduce scheduling flexibility.

More resources: More tasks can execute concurrently, reducing project duration.

Fewer resources: Tasks must be serialized, increasing completion time.

More dependencies: Fewer task orderings are possible.

Long dependency chains: Create a critical path that limits the minimum project duration.

Tight deadlines: Can make the problem infeasible even when enough resources exist.

For example, if the resource capacity were reduced from 3 to 2, T2 and T3 could no longer run simultaneously. This increases the project duration.

8. Why Backtracking Is Effective

Without pruning, \(n\) tasks may have up to:

$$ n! $$

possible orderings.

Backtracking avoids examining all permutations by rejecting a partial schedule as soon as it violates a constraint.

For example:

Choose T4

↓

Check predecessors

↓

T2 not completed → PRUNE

There is no need to construct the rest of that invalid schedule.

Thus, pruning can dramatically reduce the practical search space.

9. NP-Hard Complexity

The Resource-Constrained Project Scheduling Problem (RCPSP) is NP-hard.

The difficulty comes from simultaneously deciding:

Which task should execute next?

When should it execute?

Which resources should be assigned?

How should precedence constraints be satisfied?

How can project completion time be minimized?

For \(n\) tasks, the number of possible task orderings can grow approximately as:

$$ O(n!) $$

Therefore, exhaustive search becomes impractical for large projects.

Backtracking has exponential/worst-case factorial-scale search behavior, but pruning, dependency analysis, lower bounds, and good task-ordering heuristics can make it practical for small and medium-sized instances.

Conclusion

A backtracking scheduler provides an exact solution by systematically exploring feasible task arrangements. Precedence checking, resource pruning, lower-bound pruning, and symmetry reduction eliminate invalid or non-promising schedules early. Although project scheduling is NP-hard and has exponential worst-case complexity, these pruning techniques significantly improve practical efficiency while preserving optimality.